## Sheet1
HAZARD ABATEMENT LOG (HAL) - EXAMPLE
Reference: MCO 5100.29C, Vol 6, Ch 3, 0305, (B), (3), (a) - (h)
UNIT: | 3D BN, 4TH MAR |  | INSTALLATION: | 29 PALMS, CA (MCAGCC) |  | GSO / GSM: | 1STLT I. M. MARINE |  | DATE LAST UPDATED: | DD-MMM-YYYY
# | Status (Pending/Abated) | Priority (Low/Med/High) | Hazard ID Date (DD-MMM-YYYY) | Est Completion Date (~30 Days) | Location (Bldg #, Floor, Rm#) | Hazard ID'd | Violation Reference (OSHA #, ANSI #, etc.) | Risk Assessment Level (RAL) | Interim Controls I/E | Long-Term Abatement (Actions, Work Order #, Est Cost, Est Date, etc.) | Closeout Summary (Date, Actions, Cost, Status of site, etc.)
1 | PENDING | LOW | 2022-09-05 | 2022-10-05 | Bldg 1446, Flr 1, Rm# 5 (Kilo Co Office) | Damaged / Burned Out Extension Cords | 1910.334(a)(2)(ii) - Defective or damaged item shall be removed from service and no employee may use it | Prob: C - Occasional Sev: III - Moderate RAL: MED | 1) Removed/disposed of damaged extension cords 2) Directed Kilo Co to supply for new extension cords 3) Supply was short (2) extension cords, new order placed | 1) Supply ordering more extension cords (Est arrival: 5 Oct 22) 2) Supply utilized safety funding codes for order 3) Supply will keep extension cords on hand for future replacements 4) Cost per extension cord (GSA): $22.35/extension cord outlet | 1) Pending shipment arrival (5 Oct 22)